## Instructions
Instructions:
1 | This document is created to help PAC track the progress of construction by tracking completed conductor stringing sections.
2 | This document represents where the phase conductors are deadending.
3 | As needed, insert more rows, just be conscientious of continuity of numbers and formulas among cells within a column.
4 | On the 'HIS Data' tab, paste the respective columns from the native HIS.
| A. | Hendrix framings that deadend primary will fill the cell red to act as a flag.
| B. | These cells, in conjunction with OMS, KMZ, PLS, etc. will be used to determine the conductor pulling sections.
5 | On the 'Pulling Section Tracker' tab, POWER will only be responsible for the grey cells.
| A. | The 'Length (ft)' can be quickly grabbed from a KMZ.
| B. | The 'Cable Size' is a drop down to select from.
| C. | The columns 'Total Structures' & 'Replacement & New Poles' are to be manually counted and revised. Please note that poles should not be re-counted. The sum of the poles in these columns should equal the sum of poles on your project.
| D. | The column 'Small Wire Removal' is to be the total length in that section that has small conductor (less than #2, #2 is ok) in that pulling section. Can be pulled off RIC tab for ease.
6 | The white "Completed" cell has a formula that automatically generates a value when a section of line is marked as energized. The cell will tally the total footage of all line segments that have been marked as energized.
7 | Store native excel file in PW.
8 | For QAQC purposes print 'HIS Data' & 'Pulling Section Tracker' tabs to one PDF file.
9 | For submittal to PAC send native excel file.
10 | Once project awarded, POWER to complete & pre-populate file then Lead uploads to construction SharePoint.
11 | Construction crew is to make new file every week generated from previous file and keep stored in SharePoint.
12 | Construction crew is responsible for yellow cells.

## HIS Data
This page is not intended for construction purposes
Sequence | Hendrix Primary Code | Hendrix Secondary Code | Hendrix Tertiary Code | DO NOT EDIT OR DELETE | DO NOT EDIT OR DELETE
|  |  |  | Hendrix Framings with deadended conductor | Drop Downs
|  |  |  | AC1117-03 | Pick Conductor
|  |  |  | AC1120-03 | 1 #1/0 15 kV
|  |  |  | AC1124-03 | 2 #1/0 15 kV
|  |  |  | AC1171-03 | 3 #1/0 15 kV
|  |  |  | AC1194-03 | 1 #4/0 15 kV
|  |  |  | AC1196-03 | 2 #4/0 15 kV
|  |  |  | AC1237-03 | 3 #4/0 15 kV
|  |  |  | AC1248-03 | 1 #477 15 kV
|  |  |  | AC1250-03 | 2 #477 15 kV
|  |  |  | AC1252-03 | 3 #477 15 kV
|  |  |  | AC1253-03 | 1 #795 15 kV
|  |  |  | AC1256-03 | 2 #795 15 kV
|  |  |  | AC1259-03 | 3 #795 15 kV
|  |  |  | AC1263-03 | 1 #1/0 35 kV
|  |  |  | AC1264-03 | 2 #1/0 35 kV
|  |  |  | AC1265-03 | 3 #1/0 35 kV
|  |  |  | AC1293-03 | 1 #4/0 35 kV
|  |  |  | AC1307-03 | 2 #4/0 35 kV
|  |  |  | AC1311-03 | 3 #4/0 35 kV
|  |  |  | AC1331-03 | 1 #477 35 kV
|  |  |  | AC2120-03 | 2 #477 35 kV
3 #477 35 kV
1 #795 35 kV
2 #795 35 kV
3 #795 35 kV
Completed

## Pulling Section Tracker
PLEASE WRITE PROJECT NAME HERE:
Pulling section info (poles only accounted for in one pulling section) | [8 empty] | Construction updates | [5 empty] | Pulling section info
Work order | Pull section | From SEQ | To SEQ | Length (ft) | Cable size | Total structures | Replacement & new poles | Small wire removal (ft) | Start of construction forecast/actual (mm/dd/yy) | Date of expected energization (mm/dd/yy) | # of structures replaced | Date of energization complete (mm/dd/yy) | Date of removals complete (mm/dd/yy) | Issues/comments | EST page number for start of pulling section | All sequences (listed sequentially) within pulling section
testWO | PS1 | 2020 -> 2030 | 5R234-1/0 ACSR-1PH | 77.90 | 1 77.90 | 0 | 0 | 0
testWO | PS5 | 2130 -> 2140 | 5R234-1/0 ACSR-1PH | 88.30 | 1 88.30 | 0 | 0 | 0
testWO | PS8 | 2210 -> 2220 | 5R234-1/0 ACSR-1PH | 89.10 | 1 89.10 | 0 | 0 | 0
testWO | PS11 | 2350 -> 2360 | 5R234-1/0 ACSR-1PH | 93.00 | 1 93.00 | 0 | 0 | 0
testWO | PS14 | 2420 -> 2430 | 5R234-1/0 ACSR-1PH | 83.40 | 1 83.40 | 0 | 0 | 0
testWO | PS22 | 2670 -> 2760 | 5R234-1/0 ACSR-1PH | 1208.50 | 1 1208.50 | 0 | 0 | 0
testWO | PS23 | 2670 -> 2680 | 5R234-1/0 ACSR-1PH | 138.80 | 1 138.80 | 0 | 0 | 0
testWO | PS30 | 2730 -> 2750 | 5R234-1/0 ACSR-1PH | 462.10 | 1 462.10 | 0 | 0 | 0
testWO | PS33 | 2760 -> 2790 | 5R234-1/0 ACSR-1PH | 223.10 | 1 223.10 | 0 | 0 | 0
testWO | PS34 | 2760 -> 2770 | 5R234-1/0 ACSR-1PH | 57.30 | 1 57.30 | 0 | 0 | 0
testWO | PS43 | 2790 -> 2880 | 5R234-1/0 ACSR-1PH | 959.80 | 1 959.80 | 0 | 0 | 0
testWO | PS44 | 2790 -> 2810 | 5R234-1/0 ACSR-1PH | 606.40 | 1 606.40 | 0 | 0 | 0
testWO | PS47 | 2880 -> 2890 | 5R234-1/0 ACSR-1PH | 79.50 | 1 79.50 | 0 | 0 | 0
testWO | PS50 | 2030 -> 2040 | 5R234-1/0 ACSR-1PH | 267.00 | 1 267.00 | 0 | 0 | 0
testWO | PS53 | 2090 -> 2080 | 5R234-1/0 ACSR-1PH | 286.90 | 1 286.90 | 0 | 0 | 0
testWO | PS56 | 2110 -> 2080 | 5R234-1/0 ACSR-1PH | 756.80 | 1 756.80 | 0 | 0 | 0
testWO | PS59 | 2140 -> 2150 | 5R234-1/0 ACSR-1PH | 363.20 | 1 363.20 | 0 | 0 | 0
testWO | PS62 | 2150 -> 2170 | 5R234-1/0 ACSR-1PH | 549.90 | 1 549.90 | 0 | 0 | 0
testWO | PS66 | 2170 -> 2180 | 5R234-1/0 ACSR-1PH | 32.10 | 1 32.10 | 0 | 0 | 0
testWO | PS69 | 2180 -> 2190 | 5R234-1/0 ACSR-1PH | 328.70 | 1 328.70 | 0 | 0 | 0
testWO | PS72 | 2220 -> 2230 | 5R234-1/0 ACSR-1PH | 271.10 | 1 271.10 | 0 | 0 | 0
testWO | PS75 | 2280 -> 2250 | 5R234-1/0 ACSR-1PH | 1244.80 | 1 1244.80 | 0 | 0 | 0
testWO | PS77 | 2250 -> 2240 | 5R234-1/0 ACSR-1PH | 105.60 | 1 105.60 | 0 | 0 | 0
testWO | PS79 | 2300 -> 2290 | 5R234-1/0 ACSR-1PH | 262.70 | 1 262.70 | 0 | 0 | 0
testWO | PS81 | 2290 -> 2280 | 5R234-1/0 ACSR-1PH | 363.40 | 1 363.40 | 0 | 0 | 0
testWO | PS86 | 2320 -> 2310 | 5R234-1/0 ACSR-1PH | 217.60 | 1 217.60 | 0 | 0 | 0
testWO | PS88 | 2310 -> 2290 | 5R234-1/0 ACSR-1PH | 55.70 | 1 55.70 | 0 | 0 | 0
testWO | PS90 | 2410 -> 2390 | 5R234-1/0 ACSR-1PH | 635.30 | 1 635.30 | 0 | 0 | 0
testWO | PS93 | 2390 -> 2350 | 5R234-1/0 ACSR-1PH | 97.60 | 1 97.60 | 0 | 0 | 0
testWO | PS96 | 2360 -> 2380 | 5R234-1/0 ACSR-1PH | 772.80 | 1 772.80 | 0 | 0 | 0
testWO | PS99 | 2430 -> 2440 | 5R234-1/0 ACSR-1PH | 291.80 | 1 291.80 | 0 | 0 | 0
testWO | PS102 | 2440 -> 2450 | 5R234-1/0 ACSR-1PH | 279.40 | 1 279.40 | 0 | 0 | 0
testWO | PS105 | 2530 -> 2470 | 5R234-1/0 ACSR-1PH | 1525.10 | 1 1525.10 | 0 | 0 | 0
testWO | PS108 | 2490 -> 2500 | 5R234-1/0 ACSR-1PH | 101.30 | 1 101.30 | 0 | 0 | 0
testWO | PS110 | 2540 -> 2630 | 5R234-1/0 ACSR-1PH | 1874.80 | 1 1874.80 | 0 | 0 | 0
testWO | PS112 | 2630 -> 2640 | 5R234-1/0 ACSR-1PH | 217.80 | 1 217.80 | 0 | 0 | 0
testWO | PS114 | 2640 -> 2660 | 5R234-1/0 ACSR-1PH | 147.20 | 1 147.20 | 0 | 0 | 0
testWO | PS118 | 2600 -> 2590 | 5R234-1/0 ACSR-1PH | 181.10 | 1 181.10 | 0 | 0 | 0
testWO | PS120 | 2590 -> 2580 | 5R234-1/0 ACSR-1PH | 71.50 | 1 71.50 | 0 | 0 | 0
testWO | PS122 | 2650 -> 2640 | 5R234-1/0 ACSR-1PH | 343.80 | 1 343.80 | 0 | 0 | 0
testWO | PS124 | 2770 -> 2780 | 5R234-1/0 ACSR-1PH | 195.60 | 1 195.60 | 0 | 0 | 0
testWO | PS127 | 2810 -> 2820 | 5R234-1/0 ACSR-1PH | 231.20 | 1 231.20 | 0 | 0 | 0
testWO | PS129 | 2850 -> 2840 | 5R234-1/0 ACSR-1PH | 179.30 | 1 179.30 | 0 | 0 | 0
testWO | PS132 | 2890 -> 2930 | 5R234-1/0 ACSR-1PH | 906.70 | 1 906.70 | 0 | 0 | 0
testWO | PS136 | 2930 -> 2940 | 5R234-1/0 ACSR-1PH | 55.60 | 1 55.60 | 0 | 0 | 0
testWO | PS139 | 2940 -> 2960 | 5R234-1/0 ACSR-1PH | 595.50 | 1 595.50 | 0 | 0 | 0
testWO | PS144 | 2330 -> 2340 | 5R234-1/0 ACSR-1PH | 419.40 | 1 419.40 | 0 | 0 | 0
testWO | PS147 | 1210 (M1) -> 2670 | 5R234-1/0 ACSR-3PH | 12603.30 | 3 4201.10 | 0 | 0 | 0
testWO | PS157 | 068073/00 13/007 -> 068073/00 11/007 | 68073-397 ACSR-3PH | 1930.80 | 3 643.60 | 0 | 0 | 0