## Instructions
Instructions:
1 | This document is created to help PAC track the progress of construction by tracking completed conductor stringing sections.
2 | This document represents where the phase conductors are deadending.
3 | As needed, insert more rows, just be conscientious of continuity of numbers and formulas among cells within a column.
4 | On the 'HIS Data' tab, paste the respective columns from the native HIS.
| A. | Hendrix framings that deadend primary will fill the cell red to act as a flag.
| B. | These cells, in conjunction with OMS, KMZ, PLS, etc. will be used to determine the conductor pulling sections.
5 | On the 'Pulling Section Tracker' tab, POWER will only be responsible for the grey cells.
| A. | The 'Length (ft)' can be quickly grabbed from a KMZ.
| B. | The 'Cable Size' is a drop down to select from.
| C. | The columns 'Total Structures' & 'Replacement & New Poles' are to be manually counted and revised. Please note that poles should not be re-counted. The sum of the poles in these columns should equal the sum of poles on your project.
| D. | The column 'Small Wire Removal' is to be the total length in that section that has small conductor (less than #2, #2 is ok) in that pulling section. Can be pulled off RIC tab for ease.
6 | The white "Completed" cell has a formula that automatically generates a value when a section of line is marked as energized. The cell will tally the total footage of all line segments that have been marked as energized.
7 | Store native excel file in PW.
8 | For QAQC purposes print 'HIS Data' & 'Pulling Section Tracker' tabs to one PDF file.
9 | For submittal to PAC send native excel file.
10 | Once project awarded, POWER to complete & pre-populate file then Lead uploads to construction SharePoint.
11 | Construction crew is to make new file every week generated from previous file and keep stored in SharePoint.
12 | Construction crew is responsible for yellow cells.

## HIS Data
This page is not intended for construction purposes
Sequence | Hendrix Primary Code | Hendrix Secondary Code | Hendrix Tertiary Code | DO NOT EDIT OR DELETE | DO NOT EDIT OR DELETE
|  |  |  | Hendrix Framings with deadended conductor | Drop Downs
|  |  |  | AC1117-03 | Pick Conductor
|  |  |  | AC1120-03 | 1 #1/0 15 kV
|  |  |  | AC1124-03 | 2 #1/0 15 kV
|  |  |  | AC1171-03 | 3 #1/0 15 kV
|  |  |  | AC1194-03 | 1 #4/0 15 kV
|  |  |  | AC1196-03 | 2 #4/0 15 kV
|  |  |  | AC1237-03 | 3 #4/0 15 kV
|  |  |  | AC1248-03 | 1 #477 15 kV
|  |  |  | AC1250-03 | 2 #477 15 kV
|  |  |  | AC1252-03 | 3 #477 15 kV
|  |  |  | AC1253-03 | 1 #795 15 kV
|  |  |  | AC1256-03 | 2 #795 15 kV
|  |  |  | AC1259-03 | 3 #795 15 kV
|  |  |  | AC1263-03 | 1 #1/0 35 kV
|  |  |  | AC1264-03 | 2 #1/0 35 kV
|  |  |  | AC1265-03 | 3 #1/0 35 kV
|  |  |  | AC1293-03 | 1 #4/0 35 kV
|  |  |  | AC1307-03 | 2 #4/0 35 kV
|  |  |  | AC1311-03 | 3 #4/0 35 kV
|  |  |  | AC1331-03 | 1 #477 35 kV
|  |  |  | AC2120-03 | 2 #477 35 kV
3 #477 35 kV
1 #795 35 kV
2 #795 35 kV
3 #795 35 kV
Completed

## Pulling Section Tracker
PLEASE WRITE PROJECT NAME HERE:
Pulling section info (poles only accounted for in one pulling section) | [8 empty] | Construction updates | [5 empty] | Pulling section info
Work order | Pull section | From SEQ | To SEQ | Length (ft) | Cable size | Total structures | Replacement & new poles | Small wire removal (ft) | Start of construction forecast/actual (mm/dd/yy) | Date of expected energization (mm/dd/yy) | # of structures replaced | Date of energization complete (mm/dd/yy) | Date of removals complete (mm/dd/yy) | Issues/comments | EST page number for start of pulling section | All sequences (listed sequentially) within pulling section